## Sheet1
Task Name | Duration | Start | Finish
Software Development | 80.75 days | Wed 2/1/23 | Wed 5/24/23
Scope | 3.5 days | Wed 2/1/23 | Mon 2/6/23
Determine project scope | 4 hrs | Wed 2/1/23 | Wed 2/1/23
Secure project sponsorship | 1 day | Wed 2/1/23 | Thu 2/2/23
Define preliminary resources | 1 day | Thu 2/2/23 | Fri 2/3/23
Secure core resources | 1 day | Fri 2/3/23 | Mon 2/6/23
Scope complete | 0 days | Mon 2/6/23 | Mon 2/6/23
Analysis/Software Requirements | 14 days | Mon 2/6/23 | Fri 2/24/23
Conduct needs analysis | 5 days | Mon 2/6/23 | Mon 2/13/23
Draft preliminary software specifications | 3 days | Mon 2/13/23 | Thu 2/16/23
Develop preliminary budget | 2 days | Thu 2/16/23 | Mon 2/20/23
Review software specifications/budget with team | 4 hrs | Mon 2/20/23 | Mon 2/20/23
Incorporate feedback on software specifications | 1 day | Tue 2/21/23 | Tue 2/21/23
Develop delivery timeline | 1 day | Wed 2/22/23 | Wed 2/22/23
Obtain approvals to proceed (concept, timeline, budget) | 4 hrs | Thu 2/23/23 | Thu 2/23/23
Secure required resources | 1 day | Thu 2/23/23 | Fri 2/24/23
Analysis complete | 0 days | Fri 2/24/23 | Fri 2/24/23
Design | 14.5 days | Fri 2/24/23 | Thu 3/16/23
Review preliminary software specifications | 2 days | Fri 2/24/23 | Tue 2/28/23
Develop functional specifications | 5 days | Tue 2/28/23 | Tue 3/7/23
Develop prototype based on functional specifications | 4 days | Tue 3/7/23 | Mon 3/13/23
Review functional specifications | 2 days | Mon 3/13/23 | Wed 3/15/23
Incorporate feedback into functional specifications | 1 day | Wed 3/15/23 | Thu 3/16/23
Obtain approval to proceed | 4 hrs | Thu 3/16/23 | Thu 3/16/23
Design complete | 0 days | Thu 3/16/23 | Thu 3/16/23
Development | 21.75 days | Fri 3/17/23 | Mon 4/17/23
Review functional specifications | 1 day | Fri 3/17/23 | Fri 3/17/23
Identify modular/tiered design parameters | 1 day | Mon 3/20/23 | Mon 3/20/23
Assign development staff | 1 day | Tue 3/21/23 | Tue 3/21/23
Develop code | 15 days | Wed 3/22/23 | Tue 4/11/23
Developer testing (primary debugging) | 15 days | Mon 3/27/23 | Mon 4/17/23
Development complete | 0 days | Mon 4/17/23 | Mon 4/17/23
Testing | 48.75 days | Fri 3/17/23 | Wed 5/24/23
Develop unit test plans using product specifications | 4 days | Fri 3/17/23 | Wed 3/22/23
Develop integration test plans using product specifications | 4 days | Fri 3/17/23 | Wed 3/22/23
Unit Testing | 15 days | Mon 4/17/23 | Mon 5/8/23
Review modular code | 5 days | Mon 4/17/23 | Mon 4/24/23
Test component modules to product specifications | 2 days | Mon 4/24/23 | Wed 4/26/23
Identify anomalies to product specifications | 3 days | Wed 4/26/23 | Mon 5/1/23
Modify code | 3 days | Mon 5/1/23 | Thu 5/4/23
Re-test modified code | 2 days | Thu 5/4/23 | Mon 5/8/23
Unit testing complete | 0 days | Mon 5/8/23 | Mon 5/8/23
Integration Testing | 12 days | Mon 5/8/23 | Wed 5/24/23
Test module integration | 5 days | Mon 5/8/23 | Mon 5/15/23
Identify anomalies to specifications | 2 days | Mon 5/15/23 | Wed 5/17/23
Modify code | 3 days | Wed 5/17/23 | Mon 5/22/23
Re-test modified code | 2 days | Mon 5/22/23 | Wed 5/24/23
Integration testing complete | 0 days | Wed 5/24/23 | Wed 5/24/23
Training | 45.75 days | Fri 3/17/23 | Fri 5/19/23
Develop training specifications for end users | 3 days | Fri 3/17/23 | Tue 3/21/23
Develop training specifications for helpdesk support staff | 3 days | Fri 3/17/23 | Tue 3/21/23
Identify training delivery methodology (computer based training, classroom, etc.) | 2 days | Fri 3/17/23 | Mon 3/20/23
Develop training materials | 3 wks | Mon 4/17/23 | Mon 5/8/23
Conduct training usability study | 4 days | Mon 5/8/23 | Fri 5/12/23
Finalize training materials | 3 days | Fri 5/12/23 | Wed 5/17/23
Develop training delivery mechanism | 2 days | Wed 5/17/23 | Fri 5/19/23
Training materials complete | 0 days | Fri 5/19/23 | Fri 5/19/23